## problems
Risk Management Plan - problems occured
Risk ID | Overall Priority | Topic | Risk Description | Probability of Occurrence | Consequence | Impact | Risk Mitigation Strategy | Mitigation Action assigned to | Risk identified by person | Risk Identified on date | Status | Last change | What was changed | Planned Closing Date | Actual closing date | Reason to Close | Timeframe | Done Risk Mitigation Action(s)
1 | 0 | Technology |  | 1
2 | 0
3 | 0
4 | 0
5 | 0
6 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## open risks
Risk Management Plan - open risks
Risk ID | Overall Priority | Topic | Risk Description | Probability of Occurrence | Consequence | Impact | Risk Mitigation Strategy | Mitigation Action assigned to | Risk identified by person | Risk Identified on date | Status | Last change | What was changed | Planned Closing Date | Actual closing date | Reason to Close | Timeframe | Done Risk Mitigation Action(s)
1 | 3 | Technology | Failure of the database server to load information from the user or quizzes. | 1 | Personal information from the user or quizzes information can't be loaded | 3
2 | 2 | Customer | The interface of the app is complicated. | 2 | Customer won"t be able to play the game as it is supposed to be. | 1
3 | 6 | Skill | Lack of knowledge from the team members on how to deal with the technologies used to deveop the project. | 2 | Project development may be compromised. | 3
4 | 6 | Project | Lack of time to develop all planned and desired functions. | 3 | Final product may not me so rich in functionalities as it was planned. | 2
5 | 6 | Technology | If the customer loses connection during the play of the game or the creation of a quizz. | 2 | Result of the game may not be saved | 3
6 | 4 | Process | Insufficient time to implement the app on all platforms. | 2 | The game won't be available on all planned platforms. | 2
7 | 3 | Customer | Possibility of too many users simultaneously. | 1 | Overload of the server. | 3
8 | 0
9 | 0
10 | 0
11 | 0
12 | 0
13 | 0
14 | 0
15 | 0
16 | 0
17 | 0
18 | 0
19 | 0
20 | 0
21 | 0
22 | 0
23 | 0
24 | 0
25 | 0
26 | 0
27 | 0
28 | 0
29 | 0
30 | 0

## closed risks
Risk Management Plan - open risks
Risk ID | Overall Priority | Topic | Risk Description | Probability of Occurrence | Consequence | Impact | Risk Mitigation Strategy | Mitigation Action assigned to | Risk identified by person | Risk Identified on date | Status | Last change | What was changed | Planned Closing Date | Actual closing date | Reason to Close | Timeframe | Done Risk Mitigation Action(s)
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## How to use
How to use:
- Fill your risk with mitigation in the folder 'open risk'
- If a risk can be closed move it to the folder 'closed risks'
- If a problem occures out of a risk, than copy it to 'problems'
- Use '#data#' as data-storage to fill the combo-boxes Topic, Impact, Occurance and person with data
- the 'Overall Priority' is a calculation with 'Probability of Occurrence' (E) and 'Impact' (G) [E*G]
-> you can add numbers for this columns (#data#) if you need to have more detail

## _data_
Meaning of Probability and Impact numbers | Probability of Occurrence | Impact | Topic | Persons | Status
low -> | 1 | 1 | Customer |  | open
middle -> | 2 | 2 | Project |  | mitigated for
high -> | 3 | 3 | Process |  | closed
|  |  | Technology |  | occured
Product
Skill

## Revision
Risk list
Revision History
Rev. no. | State | Date | Comments | Author
1 | in work | 10.10.2020 | Initial version | Andrei Martins