## Product Backlog
ID | Description | Priority | Effort (hours) |  | Status | Remark
|  |  | estimated | required
1 | As a user, I want to be able to be able to log in so that I can play the game. | 3 | 5 |  | planned
2 | As a user, I want to be able to register an account so that I can play the game. | 3 | 5 |  | planned
3 | As a user, I want to be able to create a quiz so that I can use it for self studying. | 3 | 10 |  | planned
4 | As a user, I want to be able to participate in a quiz so that I can answer the questions. | 3 | 15 |  | planned
5 | As a user, I want to be able to create a quiz and share it so that other people can participate. | 3 | 20 |  | planned
6 | As a user, I want to be able to see how good my knowledge is compared to other users. | 2 | 10 |  | planned
7 | As a user, I want to be able to select the time to answer each question of my quiz, so that I can control the overall time to finish the quiz. | 2 | 5 |  | planned
8 | As a user, I want to be able to select the quantity of questions of that my quiz will have, so that I control the overall time to finish the quiz. | 2 | 10 |  | planned
9 | As a user, I want to be able to schedule when the quiz could be open for other people to participate. | 1 | 15 |  | planned
10 | As a user, I want to be able to select the language so that I can play with my prefered language. | 1 | 8 |  | planned
11 | As a user, I want to be able to create a quiz game that supports multiple choices and short answers, so that I can control the type of the question. | 1 | 10 |  | planned
12 | As a user, I want to be able to play in a Phone or Web-Browser so that I have more flexibility in which device I want to play. | 1 | 5 |  | planned
13 | As a user, I want to be able to see if my answer to a question was correct or not. | 2 | 5 |  | planned
14 | As a user, I want to be able to play the game in the Phone in Portrait or Landscape mode, so that I can use my preferred view method. | 2 | 3 |  | planned

## Sprint 1 - Quizigma
Sprint 1
Starts | 2020-11-05
Ends | 25/11/2020
Overall Goal | Create the basic functions of the application.
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
1 | As a user, I want to be able to be able to log in so that I can play the game. | User is able to login with an already registered account. |  |  |  | to do
2 | As a user, I want to be able to register an account so that I can play the game. | User is able to create a new account. |  |  |  | to do
3 | As a user, I want to be able to create a quiz so that I can use it for self studying. | User is able to play his/her own game and get which answer were answred right. |  |  |  | to do
4 | As a user, I want to be able to participate in a quiz so that I can answer the questions. | User is able to participate in game created by another user using an ID shared by the creator of the game. |  |  |  | to do
5 | As a user, I want to be able to create a quiz and share it so that other people can participate. | User is able to create a quiz with as many questions as he/she likes and share its ID so that other users can participate. |  |  |  | to do
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Persons
|  |  | estimated | required

## Sprint 1 Template
Sprint 1
Starts | 2018-11-08
Ends | 2018-11-28
Overall Goal | Improve user profile functionality
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
1 | As a registered user I want to set-up a personal profile page to present myself. | User can define and view profile page with profile picture and self description. |  |  |  | in process
done
to do
accepted
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Person(s)
|  |  | estimated | required
1 | Extend database with fields for profile info | 1 | 3 | 4.5 | done | Philipp Graf
2 | Develop form to fill in profile data in HTML | 1 | 6 |  | in process | Anja Müller
3 | Add form and logic for save / edit to application | 1 | 3 |  | to do